## 📋 Instructions
Project Time Sheet — User Guide
This file mirrors the KII GitHub Project structure. Use the "KII Tasks" sheet to manage your team's work.
Overview
Sheet: KII Tasks | Main working sheet — add, edit and track all project tasks here.
Sheet: Team (hidden) | Stores the list of GitHub team members used for the Assignee dropdown.
Sheet: Instructions | This page.
Column Guide
# | Auto row reference number. Fill manually when adding a new task.
Title | Short, clear name for the task. Keep it actionable (e.g. "Fix login bug").
Description | Detailed explanation of what needs to be done.
Assignee | Click the cell and pick a team member from the dropdown list.
Status | Current state of the task. Pick from dropdown: Backlog → Ready → In progress → In review → Done
Priority | Urgency level. Pick from dropdown: Critical / High / Medium / Low
Size | Effort estimate in T-shirt sizes: XS / S / M / L / XL
Estimate (h) | Numeric estimate in hours (e.g. 4). Used for capacity planning.
Start Date | Date the task is planned to start (format: YYYY-MM-DD).
Target Date | Deadline or expected completion date (format: YYYY-MM-DD).
Labels | Free-text tags for grouping (e.g. "bug, frontend, urgent").
Notes | Any extra context, blockers, or links relevant to the task.
How to Add a New Task
Step 1 | Go to the "KII Tasks" sheet.
Step 2 | Scroll to the first empty row after the last task.
Step 3 | Fill in #, Title and Description at minimum.
Step 4 | Click the Assignee cell → select a team member from the dropdown.
Step 5 | Set Status to "Backlog" or "Ready" to start.
Step 6 | Fill in Priority, Size, dates and Estimate as needed.
Tips & Tricks
Filter by assignee | Click the dropdown arrow on the "Assignee" header to filter tasks by person.
Filter by status | Use the "Status" column filter to see only In-progress or Done tasks.
Sort by date | Click "Target Date" header to sort tasks by deadline.
Colour coding | Status and Priority cells are colour-coded — no setup needed, just pick from the dropdown.
Adding team members | To add a new member, unhide the "Team" sheet, add their GitHub username in column A, then hide it again.

## KII Tasks
# | Title | Description | Assignee | Status | Priority | Size | Estimate (h) | Start Date | Target Date | Labels | Notes
1 | Example task 1 | Brief description of what needs to be done | MauricioDuqueABI | Backlog | Medium | M | 4 | 2026-07-01 | 2026-07-05 | feature
2 | Example task 2 | Another example task | ashiqul-abi | Ready | High | S | 2 | 2026-07-03 | 2026-07-04 | bug | Urgent
3 | Example task 3 | Work in progress example | dilinaabi | In progress | Low | L | 8 | 2026-06-28 | 2026-07-10 | improvement

## Team (hidden)
ashiqul-abi
dilinaabi
Ksomjee
MauricioDuqueABI
mpatel0975
ThongHHuynhh