## 📋 Instructions
Project Time Sheet — User Guide
This file mirrors the KII GitHub Project structure. Use the "KII Tasks" sheet to manage your team's work.
Overview
Sheet: KII Tasks | Main working sheet — add, edit and track all project tasks here.
Sheet: Team (hidden) | Stores the list of GitHub team members used for the Assignee dropdown.
Sheet: Instructions | This page.
Column Guide
# | Auto row reference number. Fill manually when adding a new task.
Title | Short, clear name for the task. Keep it actionable (e.g. "Fix login bug").
Description | Detailed explanation of what needs to be done.
Assignee | Click the cell and pick a team member from the dropdown list.
Status | Current state of the task. Pick from dropdown: Backlog → Ready → In progress → In review → Done
Priority | Urgency level. Pick from dropdown: Critical / High / Medium / Low
Size | Effort estimate in T-shirt sizes: XS / S / M / L / XL
Estimate (h) | Numeric estimate in hours (e.g. 4). Used for capacity planning.
Start Date | Date the task is planned to start (format: YYYY-MM-DD).
Target Date | Deadline or expected completion date (format: YYYY-MM-DD).
Labels | Free-text tags for grouping (e.g. "bug, frontend, urgent").
Notes | Any extra context, blockers, or links relevant to the task.
How to Add a New Task
Step 1 | Go to the "KII Tasks" sheet.
Step 2 | Scroll to the first empty row after the last task.
Step 3 | Fill in #, Title and Description at minimum.
Step 4 | Click the Assignee cell → select a team member from the dropdown.
Step 5 | Set Status to "Backlog" or "Ready" to start.
Step 6 | Fill in Priority, Size, dates and Estimate as needed.
Tips & Tricks
Filter by assignee | Click the dropdown arrow on the "Assignee" header to filter tasks by person.
Filter by status | Use the "Status" column filter to see only In-progress or Done tasks.
Sort by date | Click "Target Date" header to sort tasks by deadline.
Colour coding | Status and Priority cells are colour-coded — no setup needed, just pick from the dropdown.
Adding team members | To add a new member, unhide the "Team" sheet, add their GitHub username in column A, then hide it again.

## KII Tasks
# | Title | Description | Assignee | Status | Priority | Size | Estimate (h) | Start Date | Target Date | Labels | Notes | Scope
1 | When estop, disable the start button | **Category:** Prevent to start from Katana when the E-stop is activated | dilinaabi | Backlog | High | [6 empty] | Katana
2 | When guard stop, start button is still disabled/wont do anything |  | dilinaabi | Backlog | High | [6 empty] | Katana
3 | When the door is open while picking up the tool there was no error on the UI and the conveyor just started without anything noticing |  | dilinaabi | Backlog | High | [6 empty] | Katana
4 | Need a way to show the PLC UI with |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
5 | Custom cut doesn't update the preview |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
6 | Check tolarances mm or px in the code logic |  | dilinaabi | Done | Medium | [6 empty] | Katana
7 | When katana starts, I have to change the cnv speed and hit apply, same with other OPC values the opc values were not saved on DB |  | dilinaabi | In progress | High | [6 empty] | Katana
8 | 3d preview and 2d preview rotations are different |  | dilinaabi | Backlog | Low | [6 empty] | Katana
9 | Show the current tool in the status bar right side |  | dilinaabi | Backlog | Low | [6 empty] | Katana
10 | When you change the page and come to home the current priview/last preview wont load |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
11 | Pump OPC issues - pressure was not able to set |  | dilinaabi | In progress | High | [6 empty] | Katana
12 | Demo graphics remove |  | dilinaabi | Backlog | Low | [6 empty] | Katana
13 | Special cut patterns (circles, cross+circle) are not previewing properly |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
14 | Nozzle selection is not clear. Also need to reorganize |  | dilinaabi | Backlog | Low | [6 empty] | Katana
15 | Calibration Mode: from katana when calibration mode enables it will remove all the offsets and change the robot side to calibration mode. it will also allow to point the correct tool holder |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
16 | Katana should show an error if the default user doesnt have permisions to start/execute RAPID Programs |  | dilinaabi | Backlog | High | [6 empty] | Katana
17 | Amadues ROI change from Settings |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
18 | Add a way to restart hermary using ssh commands |  | dilinaabi | Backlog | Medium | [6 empty] | Katana
19 | Evaluate and Make decision of OPC/RMQ IPC (RestAPI) | **Notes:** OPC required ABB License, no started | MauricioDuqueABI | Backlog | Medium | [6 empty] | Katana
20 | Main Layout bug fixes | **Notes:** Which? | ashiqul-abi | In progress | Medium | [6 empty] | Katana
21 | Add current recipe settings page | **Priority:** Low | ashiqul-abi | In progress | Low | [6 empty] | Katana
22 | Remove/Hide unusable demo components | **Priority:** Low | ashiqul-abi | In progress | Low | [6 empty] | Katana
23 | Bind everything properly | **Priority:** High | ashiqul-abi | In progress | High | [6 empty] | Katana
24 | Buffer to fix the other minor things on pages | **Priority:** Low | ashiqul-abi | Backlog | Low | [6 empty] | Katana
25 | Changes to multi db model to single db postgres structure | **Priority:** High | dilinaabi | Done | High | [6 empty] | Katana
26 | CSV creation, dump, backups and restore | **Priority:** High | dilinaabi | Done | High | [6 empty] | Katana
27 | Modify the database from ths UI | **Priority:** High | dilinaabi | Done | High | [6 empty] | Katana
28 | Test multicamera setup | **Notes:** It is tested in EyeQ | dilinaabi | In progress | Medium | [6 empty] | Katana
29 | Intergrate RestAPI in the capture pipeline | **Notes:** No request for BDF | ashiqul-abi | Backlog | Medium | [6 empty] | Katana
30 | Intergrate UI Web Frame |  |  | Backlog | Medium | [6 empty] | Katana
31 | Stitching fixes | **Notes:** What is the latest status of this? Need to be merge with Main branch | dilinaabi | Done | Medium | [6 empty] | Katana
32 | Use OPC To connect with PLC | **Priority:** High | MauricioDuqueABI | In progress | High | [6 empty] | Katana
33 | Use OPC To connect with Robot-controller | **Priority:** High | MauricioDuqueABI | In progress | High | [6 empty] | Katana
34 | Order of the logs from most recent to oldest + Enable logs filtering and export | **Category:** Grey lines on the scan preview **Notes:** Merged: 'Record Error' button to create a copy of the current log file [Update / UI, Branch: LaLorraine, source status: Complete]. |  | In review | Low | [6 empty] | Katana
35 | Create a permission management and user access system | **Category:** Grey lines on the scan preview **Notes:** Merged: (1) Security Manager UI — user add/edit/password change [Khurram has sample code]; (2) Configurable product-security / user-login parameters — implementable via remote support (Src: A-000741 Boulart Customer Visit). Source statuses: Security Manager UI=Complete, Config params=Backlog. | ashiqul-abi, dilinaabi | Done | High |  | 40 | 2026-04-15 | 2026-04-30 |  |  | Unity
36 | Add Katana Setting to choose zone for robtargets |  |  | Backlog | Medium | [6 empty] | Katana
37 | Comm to PLC not through Robot | **Notes:** [Feature / General] ¦ Eliminate comm between Katana and PLC through Robot - have it be direct bidirectional. In progress because one way communication of statistics from PLC to Katana has already been established. |  | In progress | Medium | [6 empty] | Katana
38 | Custum cuts can be generated by loading points from Recipe File; Custom cut generator to be build and included on K2 | **Notes:** [Update / Motion] ¦ Branch: LaLorraine |  | In progress | Medium | [6 empty] | Katana
39 | Audit Trail (User Action) Logging | **Notes:** [Update / General] ¦ Branch: LaLorraine |  | In progress | Medium | [6 empty] | Katana
40 | Pop-up description of each setting for Katana | **Notes:** [Update / UI] ¦ Give a pop-up drawing explanation for each setting to be better understandable for the user. For some of the more complex movements, we could record a simple animation using RobotStudio sim and the CAD geometry |  | In progress | Low | [6 empty] | Katana
41 | Adding a view which shows the directions (x, y, and z) as well as the movement directions to facilitate manual operations and corrections of cutting parameters | **Notes:** In Unity Katana 1.5. Prepared offline and pushed. No downtime required ¦ Src: A-000741 - Boulart - Customer Visit Items_Nov 2034 |  | In progress | Low | [6 empty] | Katana
42 | Toggle for for photoeye vs continuous scanning | **Notes:** [Update / Vision] ¦ Should have a switch in Setting to show or hid this ¦ Branch: Mecatherm |  | Backlog | Medium | [6 empty] | Katana
43 | Scaling for 'Scoring Layout' Cut Preview - cut vs. ellips scaling - autoscale entire image to fit in box | **Notes:** [Bug / UI] ¦ To be in Subra Task Completion First Review ¦ Branch: dev\sm\addscalingforscoringlayoutpreview |  | Backlog | Medium | [6 empty] | Katana
44 | Add Katana Setting to Change Number of Points for Cuts (to balance Contour following vs speed) | **Notes:** [Feature / Motion] ¦ Default360view.xaml ¦ Branch: Wegmans |  | Backlog | Low | [6 empty] | Katana
45 | Add waterjet offsets and waterjet specific options | **Notes:** [Update / UI] ¦ Branch: LaLorraine |  | Backlog | Medium | [6 empty] | Katana
46 | Added UI adjustable intensity threshold and background threshold | **Notes:** [Update / UI] ¦ Branch: Mecatherm |  | Backlog | Medium | [6 empty] | Katana
47 | Tray Height Signal | **Notes:** [Update / General] ¦ Branch: LaLorraine |  | Backlog | Medium | [6 empty] | Katana
48 | Add indexing mode to cycle boards | **Notes:** [Update / General] ¦ Branch: Mecatherm |  | Backlog | Medium | [6 empty] | Katana
49 | Added first connected rob interface for fail over | **Notes:** [Fix / General] ¦ Not required once direct com to plc is implemented ¦ Branch: LaLorraine |  | Backlog | Medium | [6 empty] | Katana
50 | Setting scroll bar is always visible, don’t have to login to scroll and check the settings; possibly get rid of scroll | **Notes:** [Update / UI] ¦ Should be complete ¦ Branch: Main |  | Backlog | Low | [6 empty] | Katana
51 | Review RobotsEnabled Settings - Should this be removed? |  | Ksomjee | Backlog | Low | [6 empty] | Katana
52 | Katana Shop Build Instructions with Settings Description | **Notes:** [Documentation / General] ¦ Carlee has started this as an exhaustive document - need to make a startup checklist | Ksomjee | Backlog | Low | [6 empty] | Katana
53 | Information displayed completely, no cut-outs (ultrasonic tab). This is resolution dependent- sometimes certain text gets cut off in certain views | **Notes:** [Fix / UI] |  | Backlog | Low | [6 empty] | Katana
54 | Should we change the imaging so that we can do more than two images at any given time | **Notes:** [Feature / Vision] ¦ To Investigate |  | Backlog | Low | [6 empty] | Katana
55 | Intensity Threshold Only Changing on Katana Program Start | **Notes:** [Fix / UI] ¦ Branch: Mecatherm |  | Backlog | Medium | [6 empty] | Katana
56 | Fixed Rotation Selectable (On/off) Instead of relying on equal Length and Width; if ON then rotation can be input by user. | **Notes:** [Update / UI] ¦ Add setting to show/hide this toggle switch on the UI ¦ Branch: LaLorraine |  | Backlog | Low | [6 empty] | Katana
57 | Recipe Dependant Scan Length | **Notes:** [Fix / Vision] ¦ Branch: LaLorraine |  | Backlog | Medium | [6 empty] | Katana
58 | Work area begining and end dynamicly adjest to the convayor speed | **Priority:** High |  | Backlog | High | [6 empty] | Katana
59 | Setup PC or PLC as NTP server | **Priority:** High |  | Backlog | High | [6 empty] | Katana
60 | Advanced angle finding for large bounding boxes using sampling lines | **Notes:** [Update / Vision] ¦ Not implimented in production. Onsite testing only ¦ Branch: Wegmans |  | Backlog | Low | [6 empty] | Katana
61 | Ensure Drag Cuts use same implementation of minz-cutdepth as Plunge | **Notes:** [Bug / Motion] ¦ Found at JJ, Applied to Mecatherm ¦ Branch: Bimbo |  | Backlog | Medium | [6 empty] | Katana
62 | Updating the tool definition for proper standards | **Priority:** High |  | Backlog | High | [6 empty] | Katana
63 | When inputing a value to a setting, add a button to accept the change. (confirm pop-up) | **Priority:** High |  | Backlog | High | [6 empty] | Katana
64 | Katana should read the camera settings and change the software ROI values | **Priority:** High |  | Backlog | High | [6 empty] | Katana
65 | Mecatherm - Dip Tank Control on UI; Intergrate Katana with PLC | **Notes:** [Feature / UI] |  | Backlog | Medium | [6 empty] | Katana
66 | WaterJet Nozzles should be ABC not 123; ensure nozzles are labeld |  |  | Backlog | Low | [6 empty] | Katana
67 | Auto recognition of camera communication loss - error handling, logging and recovery | **Notes:** [Feature / Vision] ¦ This issue came up on FGF Secretariat 2023-01-09 |  | Backlog | High | [6 empty] | Katana
68 | Katana Settings (as many as possible) should be immideatly applied by modifying a rapid variable rather than applying at scan processing time | **Notes:** [Feature / General] ¦ So that customers can see the changes right away and not have to wait for the next scan. Example of settings already implemented this way: MinZ, minRelDist, nMaxDist |  | Backlog | Medium | [6 empty] | Katana
69 | Flashing notice per robot of "appling settings" for parameters change that will only take effect on the next scan |  |  | Backlog | Low | [6 empty] | Katana
70 | Hermary 3D full color cloud map | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
71 | Smart recommendations for troubleshooting (done for EYE-Q, needs to be implemented on Katana 2.0) | **Priority:** High |  | Backlog | High | [6 empty] | Katana
72 | Smart monitoring of predictive failure of ultrasonics | **Priority:** High |  | Backlog | High | [6 empty] | Katana
73 | Scoring designer - AI score designer (from photos) - Hand drawing | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
74 | Energy conservation by shutting of laser when not in use |  |  | Backlog | Low | [6 empty] | Katana
75 | Auto path & distribution | **Category:** (automatic determination of robot path and distribution (direction of cuts, movement between cuts, movement between product and order between cuts) Benefit for the customers Reduces cost and time to add and change a recipe for us and the customer (troubleshooting) Ensures the fastest rate every time |  | Backlog | Medium | [6 empty] | Katana
76 | Ability to save recipes on a USB | **Notes:** Implement script to save to USB. An hour of remote support. CSV file already being saved. The file is currently being output on the HD everytime Katana launches. Location: C:\ProgramData\Aetherics\ABI Katana Scoring\Production Package Library\LibraryIndex.csv Prepared offline and pushed. No downtime required ¦ Src: A-000741 - Boulart - Customer Visit Items_Nov 2028 |  | Backlog | Medium | [6 empty] | Katana
77 | Inverting the vision image to match reality due to the position of the HMI | **Notes:** Complete ¦ Src: A-000741 - Boulart - Customer Visit Items_Nov 2032 |  | Backlog | Low | [6 empty] | Katana
78 | Investigate automatic fail over for various cases | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
79 | ToolChange and dip and clean in Progress | **Notes:** [Katana2] ¦ postponed to AB3 JM - Including Starting status ¦ Src: LLCZ TO DO |  | Backlog | Medium | [6 empty] | Katana
80 | Ultrasonic test button should be disabled when robot not holding us tool | **Notes:** [Katana2] ¦ JM - for later ¦ Src: LLCZ TO DO |  | Backlog | High | [6 empty] | Katana
81 | Change the FGF phantom to phantom mode | **Priority:** High |  | Backlog | High | [6 empty] | Katana
82 | make available Phantom mode for customers to use | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
83 | Simulate the encoder for robot convayor input | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
84 | System limit ranges should be changable for superadmin | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
85 | Limit range should be visible near the limit | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
86 | Communication loss shouldn't crash Katana |  |  | Backlog | High | [6 empty] | Katana
87 | warm start the robots and power cycle the cameras | **Priority:** Low |  | Backlog | Low | [6 empty] | Katana
88 | When Saving Prod Pkg ask to overwrite current package or create new | **Notes:** [Feature / UI] | Ksomjee | Done | Medium | [6 empty] | Katana
89 | Show relative length and relative spacing | **Notes:** [Fix / UI] | Ksomjee | Done | Low | [6 empty] | Katana
90 | Drive Profile should be updated to Robots/PLC on Production Package Load not Just when Start is Pressed | **Notes:** [Bug / UI] | Ksomjee | Done | Medium | [6 empty] | Katana
91 | Hide scoring settings based on selected tool (e.g. cutlength when plunge…) | **Notes:** [Update / UI] ¦ Branch: ? | MauricioDuqueABI | Done | Low | [6 empty] | Katana
92 | Fix Phantom Mode | **Notes:** [Bug / UI] |  | Done | High | [6 empty] | Katana
93 | Katana should show drive profile on Production Package View as Column AND in the Operation Panel under the Recipe Name | **Notes:** [Update / UI] | MauricioDuqueABI | Done | Low | [6 empty] | Katana
94 | When Clicking on Alarm History Onscreen Keyboard Appears | **Notes:** [Fix / UI] ¦ Found at Bimbo - Standard Windows 10 Setup ¦ Branch: Ditsch |  | Done | Medium | [6 empty] | Katana
95 | User input to define robot work area beginning and end | **Notes:** [Update / UI] ¦ Branch: LaLorraine |  | Done | Medium | [6 empty] | Katana
96 | Implement Lateral and Slice Movement in RAPID (Already on Katana) in Base RAPID | **Notes:** [Feature / Motion] ¦ Complete on Katana Main Branch |  | Done | Medium | [6 empty] | Katana
97 | Independent ROI Setttings per Camera | **Notes:** [Feature / UI] ¦ Partially implemented for two cameras at FGF |  | Done | Medium | [6 empty] | Katana
98 | Ensure the encoder trigger mode works with Amadeus cameras |  |  | Backlog | Medium | [6 empty] | Katana
99 | Relative Length of cut should scale with product width or length depending on cut angle | **Notes:** Branch: Mecatherm |  | Backlog | Medium | [6 empty] | Katana
100 | Fix and re-enable projected cuts in Vision Scan Preview (Mark cut points). | **Category:** Add direction of robot process to allow for offline path+distribution optimization (when paired with Phantom mode) |  | Backlog | Medium | [6 empty] | Katana
101 | Cleanup hard coded project specific logic branches -> convert to optional settings. | **Notes:** Subra has provided initial comments for this |  | Backlog | Low | [6 empty] | Katana
102 | Secuirty Manager UI to Allow User Add, Edit, Password Change | **Notes:** Khurram has some sample code for this |  | Done | High | [6 empty] | Katana
103 | For waterjet tooling, add a recipe dependant user input to allow selection between fixed and product dependant tooling angle. | **Notes:** Branch: Mecatherm ¦ Need to check if Mecatherm has an implementation of this already |  | Backlog | Low | [6 empty] | Katana
104 | For waterjet tooling, update cut preview based on how many nozzles are enabled. |  |  | Backlog | Low | [6 empty] | Katana
105 | Autobackup for Settings & Default Database | **Notes:** If settings file is successfully loaded, overwrite the default settings file |  | Backlog | Medium | [6 empty] | Katana
106 | UI Feature to calculate Scan Length, and Trigg Dist based on 'max product length' | **Notes:** Build in shop - will be easier if this is automatic |  | Backlog | Medium | [6 empty] | Katana
107 | Add "Record Error" button. To create a copy of the current log file | **Notes:** Branch: LaLorraine |  | Done | Medium | [6 empty] | Katana
108 | Making the configuration parameters of product security dependant user logins and security will be configurable | **Notes:** Source: A-000741 - Boulart - Customer Visit Items_Nov 2030 ¦ This can be implemented with a remote support/site visit |  | Backlog | Medium | [6 empty] | Katana
109 | Tray analysis | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 10 |  |  |  |  | Eye-Q
110 | The overlap detection/touching products | **Category:** Eye-Q Software Development | ashiqul-abi | Done | High |  | 20
111 | Product data file definition | **Category:** Eye-Q Software Development | MauricioDuqueABI | In progress | Medium |  | 20 | 2026-05-26 | 2026-06-03 |  |  | Eye-Q
112 | Restrict setting changes | **Category:** Eye-Q Software Development |  | Backlog | High | [6 empty] | Eye-Q
113 | Software stops | **Category:** Eye-Q Software Development | ashiqul-abi | Done | High |  | 10 | 2025-12-02 | 2025-12-31 |  |  | Eye-Q
114 | Total defects breakdown to be added | **Category:** Eye-Q Software Development | dilinaabi | Done | Medium |  | 30 | 2026-04-01 | 2026-04-30 |  |  | Eye-Q
115 | Rejected Products Counts | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 10 | 2026-01-01 | 2026-01-30 |  |  | Eye-Q
116 | Fix the active recipe issue (to be verified) | **Category:** Eye-Q Software Development | ashiqul-abi | Done | High |  | 10 | 2026-05-01 | 2026-05-22 |  |  | Eye-Q
117 | Enabling manual bypass for recipe selection | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 10 | 2026-01-01 | 2026-01-30 |  |  | Eye-Q
118 | Tune double rejection for post baking | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 20 | 2026-04-01 | 2026-04-30 |  |  | Eye-Q
119 | Process empty boards | **Category:** Eye-Q Software Development | ashiqul-abi | Backlog | Medium | [6 empty] | Eye-Q
120 | Add seam detection | **Category:** Eye-Q Software Development | MauricioDuqueABI | Done | High |  | 40 | 2026-05-29 | 2026-05-29 |  |  | Eye-Q
121 | Check recipe tab | **Category:** Eye-Q Software Development |  | Backlog | Low | [6 empty] | Eye-Q
122 | Deploy EyeQ in Scoring | **Category:** Eye-Q Software Development |  | Backlog | Medium | [6 empty] | Eye-Q
123 | Input for minimum acceptable distance between two product | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 20 | 2026-02-03 | 2026-02-20 |  |  | Eye-Q
124 | Have a count per recipe | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Low |  | 10 | 2026-02-03 | 2026-02-13 |  |  | Eye-Q
125 | Review with customer our current images and labels | **Category:** Eye-Q Software Development |  | Backlog | Medium | [6 empty] | Eye-Q
126 | Create an interface in the software to relabel and train automatically ML images | **Category:** Eye-Q Software Development | MauricioDuqueABI | Backlog | Medium | [6 empty] | Eye-Q
127 | QA app and ASAP Integration | **Category:** Eye-Q Software Development |  | Backlog | Medium | [6 empty] | Eye-Q
128 | Move EyeQ on Depositing | **Category:** Eye-Q Software Development |  | Backlog | Medium | [6 empty] | Eye-Q
129 | Redstone install jetson | **Category:** Eye-Q Software Development | MauricioDuqueABI | Done | Medium |  | 4 | 2026-04-14 | 2026-04-30 |  |  | Eye-Q
130 | CIELAB L* Analysis | **Category:** Eye-Q Software Development | MauricioDuqueABI, ashiqul-abi | Done | Medium |  | 60 | 2026-04-01 | 2026-06-19 |  |  | Eye-Q
131 | Multiple Amadeus 3D cameras stitching | **Category:** Eye-Q Software Development | dilinaabi, ashiqul-abi | In progress | High |  | 30 | 2026-03-02 | 2026-05-28 |  |  | Eye-Q
132 | Automatic Email Reporting | **Category:** Eye-Q Software Development | ashiqul-abi | In progress | Low |  | 20 | 2026-05-26 | 2026-05-29 |  |  | Eye-Q
133 | Auto Tick per mm calibration | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 20 | 2026-04-01 | 2026-04-17 |  |  | Eye-Q
134 | Hardware control (Blow Off, Vision Lights) | **Category:** Eye-Q Software Development | ashiqul-abi, MauricioDuqueABI | Done | Medium |  | 30 | 2026-04-01 | 2026-04-17 |  |  | Eye-Q
135 | Opc-Server / Client Certificates | **Category:** Eye-Q Software Development | dilinaabi | Done | Medium |  | 30 | 2026-04-01 | 2026-04-30 |  |  | Eye-Q
136 | Product measurements with trends | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Medium |  | 45 | 2025-12-01 | 2025-12-31 |  |  | Eye-Q
137 | Ace Basler Calibration and Stitching UI | **Category:** Eye-Q Software Development | dilinaabi | Done | Medium |  | 30 | 2025-12-02 | 2025-12-26 |  |  | Eye-Q
138 | Roboflow Integration AI | **Category:** Eye-Q Software Development | MauricioDuqueABI | Done | Medium |  | 20 | 2026-01-01 | 2026-01-23 |  |  | Eye-Q
139 | API Pontem Integration | **Category:** Eye-Q Software Development |  | In progress | Medium |  | 20 | 2026-05-01 | 2026-06-26 |  |  | Eye-Q
140 | Race Line Basler Camera Integration | **Category:** Eye-Q Software Development | MauricioDuqueABI | Done | Medium |  | 30 | 2026-04-01 | 2026-04-30 |  |  | Eye-Q
141 | Line by Line Stitching for SL1880 and Amadeus | **Category:** Eye-Q Software Development | dilinaabi, ashiqul-abi | Done | Medium |  | 40 | 2026-04-01 | 2026-04-30 |  |  | Eye-Q
142 | PLC integration Siemens and AB | **Category:** Eye-Q Software Development | MauricioDuqueABI, ashiqul-abi | Done | High |  | 25 | 2026-04-01 | 2026-04-30 |  |  | Eye-Q
143 | Separation Log from user actions | **Category:** Eye-Q Software Development | ashiqul-abi | Done | Low |  | 20 | 2026-04-01 | 2026-04-17 |  |  | Eye-Q
144 | Refactor Robot Communication | **Category:** Software Functions | MauricioDuqueABI | Done | Medium |  | 88 | 2026-02-10 | 2026-04-10 |  |  | Katana
145 | Initiate Recuritment for supplemental contractor dev role | **Category:** Software Functions | Ksomjee | Done | Low |  | 2 | 2026-01-13 | 2026-01-16 |  |  | Katana
146 | Hermary Camera - Function Block development | **Category:** Software Functions | ashiqul-abi | Done | Medium |  | 40 | 2026-01-19 | 2026-01-21 |  |  | Katana
147 | Data Interface for Katana 1.5 > 2 transition | **Category:** Software Functions | dilinaabi | Done | High |  | 100 | 2026-01-22 | 2026-02-08 |  |  | Katana
148 | Complete Web UI | **Category:** Software Functions | ashiqul-abi | Done | High |  | 110 | 2026-02-14 | 2026-04-03 |  |  | Katana
149 | Separate Back End and Front End | **Category:** Software Functions | ashiqul-abi | Done | Medium |  | 80 | 2026-02-10 | 2026-03-19 |  |  | Katana
150 | Test plan document (Hardware + software) | **Category:** Software Functions | Ksomjee | In progress | Medium |  | 40 | 2026-02-10 | 2026-03-31 |  |  | Katana
151 | Katana II robot program development (RAPID) | **Category:** Software Functions |  | Done | High |  | 80 | 2026-02-10 | 2026-03-31 |  |  | Katana
152 | Critical UI Bugs Fix | **Category:** Software Functions | ashiqul-abi | In progress | High |  | 30 | 2026-05-07 | 2026-05-13 |  |  | Katana
153 | Backend and DB Bugs Fix | **Category:** Software Functions | dilinaabi | In progress | High |  | 30 | 2026-05-07 | 2026-05-13 |  |  | Katana
154 | PLC Robot Bug Fix Communication and UDTs | **Category:** Software Functions | MauricioDuqueABI | In progress | High |  | 30 | 2026-05-08 | 2026-05-13 |  |  | Katana
155 | Smart Alarms and Intelligent Support - Development | **Category:** Software Features | Ksomjee | In progress | Medium |  | 80 | 2026-02-21 | 2026-04-01 |  |  | Katana
156 | Smart Alarms and Intelligent Support - Trouble Shooting Details | **Category:** Software Features |  | Backlog | Medium | [6 empty] | Katana
157 | Robot Metrics | **Category:** Software Features |  | Backlog | Low | [6 empty] | Katana
158 | Full Simulation | **Category:** Software Features | Ksomjee | In progress | Medium |  | 160 | 2026-02-10 | 2026-04-06 |  |  | Katana
159 | MyMecatherm Integration | **Category:** Software Features | MauricioDuqueABI | Done | Medium |  | 40 | 2026-03-10 | 2026-03-27 |  |  | Katana
160 | New screen, embedded in the vision cell | **Category:** Software Features |  | Done | Medium | [6 empty] | Katana
161 | UI features | **Category:** Software Features |  | Done | Medium | [6 empty] | Katana
162 | Web interface + remote access | **Category:** Software Features | ashiqul-abi | Done | Medium |  | 20 | 2026-04-06 | 2026-04-08 |  |  | Katana
163 | Recipe creation wizard (+ gifs/animation) | **Category:** Software Features | ashiqul-abi | Done | Medium |  | 40 | 2026-04-06 | 2026-04-11 |  |  | Katana
164 | Complete user manuals (maintenance + MyMct ready) | **Category:** Software Features | MauricioDuqueABI | In progress | Low |  | 100 | 2026-03-30 | 2026-04-16 |  |  | Katana
165 | New look and feel | **Category:** Software Features |  | Done | Medium |  | 10 | 2026-04-06 | 2026-04-15 |  |  | Katana
166 | Pump controls (recipe driven-OPC driven) | **Category:** Software Features | MauricioDuqueABI | Done | High |  | 78 | 2026-02-09 | 2026-03-20 |  |  | Katana
167 | Bakery De France Deadline | **Category:** Software Features |  | Done | High |  | 1 | 2026-03-31 | 2026-03-31 |  |  | Katana
168 | Robot Calibration Automation Support | **Category:** Capstone |  | Backlog | Medium |  | 50 |  |  |  |  | Capstone
169 | Isolate the 10 worst images of each run for training purposes | **Category:** Unity Software Development | ashiqul-abi | In progress | Medium |  | 10 | 2026-05-01 | 2026-12-31 |  |  | Unity
170 | Automatic email report | **Category:** Unity Software Development | Ksomjee | In progress | Low |  | 10 |  |  |  |  | Unity
171 | Enable a different UI and KPIs for production management | **Category:** Unity Software Development |  | Backlog | Medium | [6 empty] | Unity
172 | Image storage to be extended to more than 24 Hrs | **Category:** Unity Software Development | ashiqul-abi | Done | Medium |  | 30 | 2026-03-03 | 2026-03-27 |  |  | Unity
173 | Grey lines on the scan preview | **Category:** Unity Software Development |  | Backlog | Medium | [6 empty] | Unity
174 | Order of the logs from most recent to oldest | **Category:** Unity Software Development | ashiqul-abi | Done | Low |  | 5 | 2026-01-06 | 2026-01-16 |  |  | Unity
175 | Trigger the alarm just 3 times and stops automatically | **Category:** Unity Software Development | ashiqul-abi | Done | Medium |  | 5 | 2026-01-06 | 2026-01-23 |  |  | Unity
176 | Move to a cloud database | **Category:** Unity Software Development | ashiqul-abi | Backlog | Medium |  | 40 |  |  |  |  | Unity
177 | Create dashboard documentation | **Category:** Unity Software Development | ashiqul-abi | Done | Low |  | 20 | 2026-04-21 | 2026-04-30 |  |  | Unity
178 | Enable logs filtering and export | **Category:** Unity Software Development | ashiqul-abi | Done | Low |  | 20 | 2026-03-03 | 2026-03-20 |  |  | Unity
179 | Friendly keyboard | **Category:** Unity Software Development | ashiqul-abi | Done | Low |  | 10 | 2026-04-08 | 2026-04-24 |  |  | Unity
180 | Script update Images from Katana/EyeQ to AWS bucket | **Category:** Unity Software Development | dilinaabi | Done | Medium |  | 10 | 2026-04-01 | 2026-04-10 |  |  | Unity

## Team (hidden)
Team Member (GitHub username)
ashiqul-abi
dilinaabi
Ksomjee
MauricioDuqueABI
mpatel0975
ThongHHuynhh